## Sheet1 (hidden)
Sr. No. | Issues | Logged by | Date | Comments | Status | Owner
1 | The first sign in screen doesn't ask for a password only a service number and name, so anyone could jump on your computer and fill in the details and then tick to say they accept the code of conduct later on once the form is filled in. Not very secure. | Rebecca Parkes | 2013-06-13 | 1. All details requested on this form must be completed by the incumbents manager otherwise the request may be declined. 2. Add email and password 3. Training and comms | Open
2 | Not sure what the second screen is even for?? | Rebecca Parkes | 2013-06-13 | The first and the second screen will be merged together. eForm Portal - Rajesh | Open
3 | Is the intention that any of the fields will populate when you enter either a Service number or position number?? | Rebecca Parkes | 2013-06-13 | Yes Name will auto-populate on entering the Service No. but not other fields. Enhancement | Open
4 | 'Approver' in "Reason for Change" should read approvers name. Also if you dont fill this field in and try to move on the error actual reads "You must provide the approver's service number'. | Rebecca Parkes | 2013-06-13 |  | Open | Raja
5 | This form should read like the paper based form and have "Current Position" details and "Position moving to" details, this is not clear enough. Then there will be no chance of errors or incorrect info being put on the form. | Rebecca Parkes | 2013-06-13 | Enhancement | Open
6 | All the fields have to be populated before you can move on which is not a good idea. There are certain field that may not change while in an Acting for or On Loan relationship so these fields do not need to have anything entered. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types | Open
7 | We tested an Admin person Acting for a Snr Contract role. Firstly they would not have RDO's while acting in a Snr Contract role so we don't want that field to be a mandatory field. Also Senior Contract staff dont have pay points and we would fill in the TRP % box instead so it should be set up if pay point field is populated then the TRP doesn't need to be and visa versa. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types | Open
8 | The work phone number should have an eg underneath so they are aware of the only format that will be accepted before you can move on. | Rebecca Parkes, Trinity and Rani | 2013-06-13 |  | Open | Raja
9 | The mobile phone number field should not be a mandatory field as not all staff members have a work mobile number. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types | Open
10 | The email payslip automatically populates to the ausgrid email address. why? What if someone's email address is set up to go to another email address. Also, there is not a line for field staff employees so they can still have a paper based pay slip. Not all staff receive their payslip by email. | Rebecca Parkes | 2013-06-13 | 1. Ability to over-write the email add 2. Paper based payslip - Rajesh | Open
11 | In the acting for relationship the field for Division, Cost Centre, Branch & Section does not appear. I would want this information to be filled in if i am going to receive the form. | Rebecca Parkes | 2013-06-13 | Position must be available in SAP ¦ position form Define all mandatory and non-mandatory fields for all reason types | Open
12 | Link to the security access form does not work for substantive access after you submit the online Maintain Employment Details form. | Rebecca Parkes | 2013-06-13 | Is this required? | Open | Raja
13 | Acting for/ On loan scenario for those in VACANT POSITION - does not work. The form produces error - "You must use the auto-suggest to pick an Incumbent Name“ Rani to re-test | Rani | 2013-06-15 |  | Open | Raja
Intuitive DD
10 digit long

## Data by Reason For Change
Maintain Employment Details Form
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column73 | Column72 | Column722 | Column8 | Column9
| Acting for | On Loan | Secondment | End of Secondment | Rotational Staff | Fixed Term Ext | Internal Hire | Change of Emp Status, Hrs or Work Schedule | Band 2 Engineer Movement (does it also apply to Band 1 movements?) | Comments/Text
Reason for change
Maintain Employment Details Form Column1: Temp Assignment |  |  |  | Status Key
Maintain Employment Details Form Column1: Acting for; Maintain Employment Details Form Column2: Y |  |  |  | Pending
Maintain Employment Details Form Column1: On Loan; Maintain Employment Details Form Column3: Y |  |  |  | Finished
Maintain Employment Details Form Column1: Secondment; Maintain Employment Details Form Column4: Y |  |  |  | Question
Maintain Employment Details Form Column1: End of Secondment; Maintain Employment Details Form Column5: Y |  |  |  | Currently Mandatory
Maintain Employment Details Form Column1: Rotational Staff |  | Processes not defined - exclude from form. Claire to discuss at user group meeting.
Apprentice
Graduate
Work experience
Cadet
Traineee
Others
Maintain Employment Details Form Column1: Fixed Term - Extention; Maintain Employment Details Form Column7: Y |  | Questions to be asked - is this an individual or mass ext? If mass individual details not required.
Internal Hire | [6 empty] | Y
Change of Emp Status or Hours | [7 empty] | Y
Maintain Employment Details Form Column1: Band 2 Engineer Movement | Y
Approver | Y | Y | Y | Y |  | Y | Y | Y |  | Approver should be the 1up mgr from SAP/Wire, should be able to overwrite the approver if it is incorrect or the mgr is on leave.
Current Position
Service Number | Y | Y | Y | Y |  | Y (Non Mand) | Y | Y | Y | Fixed Term Ext - fields are only mandatory if an individual is being extended. | This being optional may cause some problems as the backend expects a service number to exist for every entry. Will have to look into this.
First Name/Last Name | Y | Y | Y | Y |  | Y (Non Mand) | Y | Y | Y
Position ID | Y | Y | Y | Y |  | Y (Non Mand) | Y | Y | Y
Position Title | Y | Y | Y | Y |  | Y (Non Mand) | Y | Y | Y
Position Moving to/Change Details
Position ID | Y | Y | Y | Y |  | Y (Non Mand) | Y |  | Y
Position Title | Y | Y | Y | Y |  | Y (Non Mand) | Y |  | Y
Start Date | Y | Y | Y | Y |  | Y (Non Mand) | Y |  | Y | NB For end of secondment start date = "return date" to previous position
Maintain Employment Details Form Column1: End Date; Maintain Employment Details Form Column2: Y; Maintain Employment Details Form Column3: Y; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column7: Y (Non Mand) | Y
Position Location | N | N | Y | Y |  |  | Y |  | Y
Maintain Employment Details Form Column1: Grade/Classification; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column5: Y; Maintain Employment Details Form Column73: Y | Y
Maintain Employment Details Form Column1: Cost Centre No & Name; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column73: Y | Y
Maintain Employment Details Form Column1: Division; Maintain Employment Details Form Column2: Y; Maintain Employment Details Form Column3: Y; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column73: Y | Y
Maintain Employment Details Form Column1: Branch; Maintain Employment Details Form Column2: Y; Maintain Employment Details Form Column3: Y; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column73: Y | Y
Maintain Employment Details Form Column1: Section; Maintain Employment Details Form Column2: Y; Maintain Employment Details Form Column3: Y; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column73: Y | Y
Maintain Employment Details Form Column1: Org Unit; Maintain Employment Details Form Column4: Y; Maintain Employment Details Form Column73: Y | Y
Employee Group and Subgroup | Y | Y | Y |  |  | Y (Non Mand) | Y | Y | Y
Maintain Employment Details Form Column1: Incumbents Name; Maintain Employment Details Form Column2: Y (Non Mand); Maintain Employment Details Form Column3: Y (Non Mand); Maintain Employment Details Form Column4: Y (Non Mand); Maintain Employment Details Form Column73: Y (Non Mand) | Y (Non Mand) | Current incumbents name if applicable | note: need to validate if name not empty, not if required
RDO Day (First Day of Scheduled RDO) | Y | Y | Y |  |  |  | Y | Y | Y
Pay Point/TRP% | Y (Non Mand) | Y (Non Mand) | Y (Non Mand) | Y (Non Mand) |  |  | Y (Non Mand) |  | Y (Non Mand)
Maintain Employment Details Form Column1: Work Schedule Rule; Maintain Employment Details Form Column4: Y (Non Mand); Maintain Employment Details Form Column73: Y (Non Mand) | Y (Non Mand)
Work Telephone | Y | Y | Y | Y |  |  | Y |  | Y
Work Mobile Number | Y (Non Mand) | Y (Non Mand) | Y (Non Mand) | Y (Non Mand) |  |  | Y (Non Mand) |  | Y (Non Mand)
Maintain Employment Details Form Column1: Does the employee work part time hours (Yes/No); Maintain Employment Details Form Column4: Y (Non Mand); Maintain Employment Details Form Column5: Y (Non Mand); Maintain Employment Details Form Column73: Y (Non Mand) | Y (Non Mand) |  | Is not set as optional when it should be due to the tie to the hours table.
Maintain Employment Details Form Column1: Update Working Hours/Day (Actual Weekly Working Hours); Maintain Employment Details Form Column4: Y (Non Mand); Maintain Employment Details Form Column5: Y (Non Mand); Maintain Employment Details Form Column73: Y (Non Mand); Maintain Employment Details Form Column72: Y | Y (Non Mand) | This is linked to Does the employee work part time hours if Yes then question re Update Working Hours/Day apear, followed by Weekly Working Hours Schedule. Would staff change working hour if they were not part time?
Approvals
Comments from Mgr | Y | Y | Y | Y |  |  | Y |  | Y
Name | Y | Y | Y | Y |  |  | Y |  | Y |  | How do we handle backend without an approver???
Date | Y | Y | Y | Y |  |  | Y |  | Y |  | Date??? What Date?
Maintain Employment Details Form Column1: Attach business case; Maintain Employment Details Form Column7: Y |  | Mandatory for all extentions, should include details of mass ext staff if applicable. | What is this? Just a file upload field?
Maintain Employment Details Form Column1: HR Admin Use Only (Backend) |  | Do HR require the checks to be built into the functionality?
Email copy to corp payroll (Yes/No) | Y | Y | Y | Y |  |  | Y |  | Y | Make sure to store the person who comlpleted the form and said yes to these questions
AD, Email & SAP Communications, infotype records added for Field User? (Yes/No) | Y | Y | Y | Y |  |  | Y |  | Y
Vacancy status changed for a Secondment? (Yes/No) | Y | Y | Y | Y |  |  | Y |  | Y
Form saved in PHF? (Yes/No) | Y | Y | Y | Y |  |  | Y |  | Y
Name | Y | Y | Y | Y |  |  | Y |  | Y
Date | Y | Y | Y | Y |  |  | Y |  | Y
Note on F4: t55422: Being reviewed - to be discussed at user group.

## Issues Log
Sr. No. | Issues | Logged by | Date | Comments | Status | Owner
1 | The first sign in screen doesn't ask for a password only a service number and name, so anyone could jump on your computer and fill in the details and then tick to say they accept the code of conduct later on once the form is filled in. Not very secure. | Rebecca Parkes | 2013-06-13 | 1. All details requested on this form must be completed by the incumbents manager otherwise the request may be declined. 2. Add email and password 3. Training and comms 19/8/13 - Make consistant with End of Employment. | Open | RK
2 | Not sure what the second screen is even for?? | Rebecca Parkes | 2013-06-13 | The first and the second screen will be merged together. 19/8/13 - Drop this screen. eForm Portal - Rajesh | Open | RK
3 | Is the intention that any of the fields will populate when you enter either a Service number or position number?? | Rebecca Parkes | 2013-06-13 | Yes Name will auto-populate on entering the Service No. but not other fields. Enhancement 19/8/13 - Form to auto-populate based on new extract. | Open | RP/RK
4 | 'Approver' in "Reason for Change" should read approvers name. Also if you dont fill this field in and try to move on the error actual reads "You must provide the approver's service number'. | Rebecca Parkes | 2013-06-13 | In Approver box include text "Enter Approvers Name" | Open | RK
5 | This form should read like the paper based form and have "Current Position" details and "Position moving to" details, this is not clear enough. Then there will be no chance of errors or incorrect info being put on the form. | Rebecca Parkes | 2013-06-13 | Enhancement 19/8/13 - If the extract has those details then this will be possible. This info has been requested as part of the extract, actual fields to be finalised. | Open | RK
6 | All the fields have to be populated before you can move on which is not a good idea. There are certain field that may not change while in an Acting for or On Loan relationship so these fields do not need to have anything entered. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types 19/8/13 - Reporting group has agreed to remove the following fields: Position Location, Email Payslip To, TT Headquarters, inc TRP% in Pay Point/TRP%, Fields Based | Open | RK
7 | We tested an Admin person Acting for a Snr Contract role. Firstly they would not have RDO's while acting in a Snr Contract role so we don't want that field to be a mandatory field. Also Senior Contract staff dont have pay points and we would fill in the TRP % box instead so it should be set up if pay point field is populated then the TRP doesn't need to be and visa versa. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types. 19/8/13 - Agreed - Refer to Data by Reason for Change worksheet. TRP to be integrated into Pay Point and made non maddatory. | Open | RK
8 | The work phone number should have an eg underneath so they are aware of the only format that will be accepted before you can move on. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | 19/18/13 - include formatting eg to provide support user. | Open | RK
9 | The mobile phone number field should not be a mandatory field as not all staff members have a work mobile number. | Rebecca Parkes, Trinity and Rani | 2013-06-13 | Define all mandatory and non-mandatory fields for all reason types 19/8/13 - Agreed make non mandatory - refer to Data by Reason for Change worksheet. | Open
10 | The email payslip automatically populates to the ausgrid email address. why? What if someone's email address is set up to go to another email address. Also, there is not a line for field staff employees so they can still have a paper based pay slip. Not all staff receive their payslip by email. | Rebecca Parkes | 2013-06-13 | Ability to over-write the email add. 19/8/13 - This field will be removed and is not the scope if this form. | Open
11 | In the acting for relationship the field for Division, Cost Centre, Branch & Section does not appear. I would want this information to be filled in if i am going to receive the form. | Rebecca Parkes | 2013-06-13 | Position must be available in SAP ¦ position form Define all mandatory and non-mandatory fields for all reason types | Open
12 | Link to the security access form does not work for substantive access after you submit the online Maintain Employment Details form. | Rebecca Parkes | 2013-06-13 | Is this required? | Open | Raja
13 | Acting for/ On loan scenario for those in VACANT POSITION - does not work. The form produces error - "You must use the auto-suggest to pick an Incumbent Name“ Rani to re-test | Rani | 2013-06-15 |  | Open | Raja
Intuitive DD
10 digit long